## 4_planning_pli
4_Planning_PLI
Add board description
FINAL REPORT IN PROGRESS
Name | Insp.Tasks | Status | Status | Final Repair | Tasks Status | NDE Timeline | All Techs | Client | Feature Type | Site Complete | Location | Joint.Length | NDE.Area | Length.NDE.Area | NWT | Project No. | PO Number | NDT Job Number | Estimate Amount | Year | Last Updated | Site | Final Report Due | QAQC Timeline | Numbers | Formula | Item ID (auto generated)
E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 | NDE, TFORM | FINAL REPORT IN PROGRESS | FINAL REPORT IN PROGRESS |  |  | 2022-03-18 - 2022-03-18, 2022-03-21 - 2022-03-21 | David Weaver, Christian Forero, Karelia Delgado | TC ENERGY |  | 2022-03-18 | 56.427476, -111.302316 |  | '- | 3 | 3.18 | E024223 | 4500439911 | 22-0016 |  | 2022 | Karelia Delgado Mar 21, 2022 01:15 PM | E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 | 2022-04-01 |  | 14 |  | 2415960154
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Christian Forero |  | 2022-03-18 | 2022-03-18 | Simon Susac Mar 21, 2022 09:24 AM |  |  | 2415960290
| TFORM | Karelia Delgado |  | 2022-03-21 | 2022-03-21 | Karelia Delgado Mar 21, 2022 01:15 PM |  |  | 2445042068
[10 empty] | 2022-03-18 | [12 empty] | 2022-04-01 |  |  | 0
QA/QC
Name | Insp.Tasks | Status | Status | Final Repair | Tasks Status | NDE Timeline | All Techs | Client | Feature Type | Site Complete | Location | Joint.Length | NDE.Area | Length.NDE.Area | NWT | Project No. | PO Number | NDT Job Number | Estimate Amount | Year | Last Updated | Site | Final Report Due | QAQC Timeline | Numbers | Formula | Item ID (auto generated)
E024223_NPS6_GregoireLatSeg1_MPID211812_Lac La Biche 3 ECEA Dig #1 | NDE, CE Samples, Welding, TFORM | QA / QC | QA / QC | RECOAT | Done |  | Karelia Delgado | TC ENERGY | EXT CORROSION | 2022-03-16 | 56.422892, -111.23064 |  | '- | 3 | 3.18 | E024223 | 4500439911 | 22-0016 |  | 2022 | Karelia Delgado Mar 18, 2022 05:20 PM | E024223_NPS6_GregoireLatSeg1_MPID211812_Lac La Biche 3 ECEA Dig #1 | 2022-03-30 |  | 14 |  | 2415960074
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE |  |  |  |  | Kaidel Martinez Mar 14, 2022 02:48 PM |  |  | 2415960266
| CE Samples |  |  |  |  | Kaidel Martinez Mar 14, 2022 02:48 PM |  |  | 2415960387
| Welding |  |  |  |  | Kaidel Martinez Mar 14, 2022 02:48 PM |  |  | 2415960515
| TFORM | Karelia Delgado | Done |  |  | Karelia Delgado Mar 21, 2022 05:29 PM |  |  | 2432140448
E024223_NPS8_GlendonLatLoop_MPID211810_Lac La Biche 5 ECEA Dig #2 | NDE, TFORMs | QA / QC | QA / QC | RECOAT | Done | 2022-03-19 - 2022-03-19, 2022-03-21 - 2022-03-21 | David Weaver, Christian Forero, Ricardo Franklin | TC ENERGY |  | 2022-03-19 | 54.326252, -111.196286 |  | '- | 3 | 4.8 | E024223 | 4500439911 | 22-0016 |  | 2022 | Ricardo Franklin Mar 21, 2022 02:31 PM | E024223_NPS8_GlendonLatLoop_MPID211810_Lac La Biche 5 ECEA Dig #2 | 2022-04-02 |  | 14 |  | 2415960276
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Christian Forero |  | 2022-03-19 | 2022-03-19 | Simon Susac Mar 21, 2022 09:23 AM |  |  | 2415960375
| TFORMs | Ricardo Franklin | Done | 2022-03-21 | 2022-03-21 | Ricardo Franklin Mar 21, 2022 02:31 PM |  |  | 2444276883
[10 empty] | 2022-03-16 to 2022-03-19 | [12 empty] | 2022-03-30 to 2022-04-02 |  |  | 0
FINALIZED - POSTED AND SENT
Name | Insp.Tasks | Status | Status | Final Repair | Tasks Status | NDE Timeline | All Techs | Client | Feature Type | Site Complete | Location | Joint.Length | NDE.Area | Length.NDE.Area | NWT | Project No. | PO Number | NDT Job Number | Estimate Amount | Year | Last Updated | Site | Final Report Due | QAQC Timeline | Numbers | Formula | Item ID (auto generated)
E024224 NPS16_Kirby_Lateral(Hanmore_Lake_CS_to_KIR67-0-LT)_GWD70140-30 | NDE, TFORM, QA/QC | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done | 2022-03-12 - 2022-03-14, 2022-03-16 - 2022-03-17 | David Weaver, Christian Forero, Ricardo Franklin, Natasha Pignalosa | TC ENERGY | EXT CORROSION | 2022-03-14 | 54.76907648, -111.88680674 | 18 | Full Joint | 18 | 7.92 | E024224 | 4500439912 | 22-0017 |  | 2022 | Ricardo Franklin Mar 21, 2022 03:37 PM | E024224 NPS16_Kirby_Lateral(Hanmore_Lake_CS_to_KIR67-0-LT)_GWD70140-30 | 2022-03-28 |  | 14 |  | 2406203073
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Christian Forero | Done | 2022-03-12 | 2022-03-14 | Ricardo Franklin Mar 16, 2022 09:57 AM |  |  | 2406203881
| TFORM | Ricardo Franklin | Done | 2022-03-16 | 2022-03-17 | Ricardo Franklin Mar 17, 2022 04:47 PM |  |  | 2413997568
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Mar 21, 2022 01:15 PM |  |  | 2445041421
E024223_NPS8_KinosisLat_MPID211813_Lac La Biche 3 ECEA Dig #2 | NDE, TForm, QA/QC | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done | 2022-03-01 - 2022-03-02, 2022-03-04 - 2022-03-08, 2022-03-08 - 2022-03-11 | David Weaver, Alejandro Dannenberg, Ricardo Franklin, Natasha Pignalosa | TC ENERGY | EXT CORROSION | 2022-03-02 | 56.181509, -110.81343 |  | '- | 3 | 5.1 | E024223 | 4500439911 | 22-0016 |  | 2022 | Ricardo Franklin Mar 11, 2022 11:25 AM | E024223_NPS8_KinosisLat_MPID211813_Lac La Biche 3 ECEA Dig #2 | 2022-03-16 |  | 14 |  | 2365098307
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Alejandro Dannenberg | Done | 2022-03-01 | 2022-03-02 | Simon Susac Mar 3, 2022 12:27 PM |  |  | 2365098537
| TForm | Ricardo Franklin | Done | 2022-03-04 | 2022-03-08 | Ricardo Franklin Mar 8, 2022 03:15 PM |  |  | 2376057205
| QA/QC | Natasha Pignalosa | Done | 2022-03-08 | 2022-03-11 | Ricardo Franklin Mar 11, 2022 11:25 AM |  |  | 2406472373
E024223_NPS10_RedwaterLat_GWD10520_MPID216464 | Coating Assessment, PLI, Mob_In, Paper Work, T-Form | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done, Done, Done | 2022-01-14 - 2022-01-15, 2022-01-16 - 2022-01-16, 2022-01-12 - 2022-01-12, 2022-01-13 - 2022-01-13 | Alejandro Dannenberg, David Weaver, Alejandro Dannenberg, David Weaver, Alejandro Dannenberg, David Weaver, Alejandro Dannenberg, David Weaver, Zeeshan Shaikh | TC ENERGY | EXT CORROSION | 2022-01-16 | 54.87268033, -114.1395191 | 9.21 | 0 to 9.28 | 9.28 | 3.96 | E024223 | 4500439911 | 22-0016 |  | 2022 | Zeeshan Shaikh Jan 26, 2022 01:55 PM | E024223_NPS10_RedwaterLat_GWD10520_MPID216464 | 2022-01-30 | 2022-01-17 - 2022-01-19 | 14 |  | 2154235369
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| Mob_In | Alejandro Dannenberg, David Weaver | Done | 2022-01-12 | 2022-01-12 | Simon Susac Jan 20, 2022 01:55 PM |  |  | 2154426777
| Paper Work | Alejandro Dannenberg, David Weaver | Done | 2022-01-13 | 2022-01-13 | Simon Susac Jan 20, 2022 01:55 PM |  |  | 2154427528
| Coating Assessment | Alejandro Dannenberg, David Weaver | Done | 2022-01-14 | 2022-01-15 | Simon Susac Jan 20, 2022 01:55 PM |  |  | 2154237578
| PLI | Alejandro Dannenberg, David Weaver | Done | 2022-01-16 | 2022-01-16 | Simon Susac Jan 20, 2022 01:55 PM |  |  | 2154238495
| T-Form | Zeeshan Shaikh | Done |  |  | Zeeshan Shaikh Jan 26, 2022 01:55 PM | 2022-01-17 | 2022-01-19 | 2177266908
TCE STN 148 - NPS 36 Suction Line | NDE, TFORM/Report, QA/QC | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done | 2022-01-28 - 2022-01-28, 2022-03-02 - 2022-03-04 | Rainier Garcia, Ricardo Franklin | TC ENERGY | MANUFACTURING | [6 empty] | M.001039 | 4500400159 | 22-0201 |  | 2022 | Natasha Pignalosa Mar 9, 2022 09:36 AM | TCE STN 148 - NPS 36 Suction Line |  |  | 14 |  | 2237011531
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | Rainier Garcia | Done | 2022-01-28 | 2022-01-28 | Ricardo Franklin Mar 4, 2022 10:32 AM |  |  | 2237016140
| TFORM/Report | Ricardo Franklin | Done | 2022-03-02 | 2022-03-04 | Ricardo Franklin Mar 4, 2022 10:32 AM |  |  | 2304044196
| QA/QC |  |  |  |  | Natasha Pignalosa Feb 16, 2022 02:28 PM |  |  | 2304126193
E024224_NPS16_PeerlessLakeLat_GWD17960_MPID214468 | Coating Assessment, PLI Assessment, Demob From Project, T-Form | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done, Done | 2022-01-17 - 2022-01-17, 2022-01-17 - 2022-01-18, 2022-01-19 - 2022-01-19, 2022-01-20 - 2022-01-20 | Alejandro Dannenberg, David Weaver, Alejandro Dannenberg, David Weaver, Alejandro Dannenberg, David Weaver, Zeeshan Shaikh, David Weaver | TC ENERGY | EXT CORROSION | 2022-01-18 | 56.89266946, -114.5378726 | 11.33 | 0 to 11.33 | 11.33 | 3.96 | E024224 | 4500439912 | 22-0017 |  | 2022 | Zeeshan Shaikh Jan 27, 2022 02:04 PM | E024224_NPS16_PeerlessLakeLat_GWD17960_MPID214468 | 2022-02-01 | 2022-01-20 - 2022-01-27 | 14 |  | 2170098531
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| Coating Assessment | Alejandro Dannenberg, David Weaver | Done | 2022-01-17 | 2022-01-17 | Simon Susac Jan 20, 2022 01:56 PM |  |  | 2170102135
| PLI Assessment | Alejandro Dannenberg, David Weaver | Done | 2022-01-17 | 2022-01-18 | Simon Susac Jan 20, 2022 01:56 PM |  |  | 2170103491
| Demob From Project | Alejandro Dannenberg, David Weaver | Done | 2022-01-19 | 2022-01-19 | Simon Susac Jan 20, 2022 01:56 PM |  |  | 2176744761
| T-Form | Zeeshan Shaikh, David Weaver | Done | 2022-01-20 | 2022-01-20 | Zeeshan Shaikh Jan 27, 2022 02:04 PM | 2022-01-20 | 2022-01-27 | 2177272532
E024223_NPS10_RedwaterLat_GWD5610_MPID186438 | NDE, Mob-In, First and Second Coating Assessment, T-Form | POSTED & SENT | POSTED & SENT | CLOCK SPRING | Done, Done, Done, Done | 2022-01-31 - 2022-01-31, 2022-01-29 - 2022-01-29, 2022-01-30 - 2022-01-30, 2022-02-08 - 2022-02-09 | Ricardo Franklin | TC ENERGY | DENT | 2022-01-31 | 54.91674227, -114.2007578 | 9.624 | 4.72 to 7.99 | 3.27 | 3.96 | E024223 | 4500439911 | 22-0016 |  | 2022 | Natasha Pignalosa Feb 11, 2022 10:49 AM | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 | 2022-02-14 |  | 14 |  | 2177491938
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| Mob-In |  | Done | 2022-01-29 | 2022-01-29 | Simon Susac Feb 1, 2022 10:18 AM |  |  | 2231661236
| First and Second Coating Assessment |  | Done | 2022-01-30 | 2022-01-30 | Simon Susac Feb 1, 2022 10:19 AM |  |  | 2231663040
| NDE |  | Done | 2022-01-31 | 2022-01-31 | Simon Susac Feb 1, 2022 10:19 AM |  |  | 2177492300
| T-Form | Ricardo Franklin | Done | 2022-02-08 | 2022-02-09 | Ricardo Franklin Mar 4, 2022 08:48 AM |  |  | 2245605020
E024223_NPS10_RedwaterLat_GWD7420_MPID215188 | NDE, CE Samples, Welding, First and Second Coating Assessment, TForm, QA/QC | POSTED & SENT | POSTED & SENT | PETRO SLEEVE | Done, Done, Done, Done, Done, Done | 2022-02-01 - 2022-02-02 | Natasha Pignalosa | TC ENERGY | EXT CORROSION | 2022-02-03 | 54.90401607, -114.1757129 | 9.33 | 0 to 9.39 | 9.33 | 3.96 | E024223 | 4500439911 | 22-0016 |  | 2022 | Natasha Pignalosa Feb 16, 2022 02:29 PM | E024223_NPS10_RedwaterLat_GWD7420_MPID215188 | 2022-02-17 |  | 14 |  | 2177492319
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| First and Second Coating Assessment |  | Done | 2022-02-01 | 2022-02-02 | Natasha Pignalosa Feb 16, 2022 02:29 PM |  |  | 2232160056
| NDE |  | Done |  |  | Natasha Pignalosa Feb 16, 2022 02:29 PM |  |  | 2177492642
| CE Samples |  | Done |  |  | Natasha Pignalosa Feb 16, 2022 02:29 PM |  |  | 2177493003
| Welding |  | Done |  |  | Natasha Pignalosa Feb 16, 2022 02:29 PM |  |  | 2177493602
| TForm |  | Done |  |  | Natasha Pignalosa Feb 16, 2022 02:29 PM |  |  | 2258324879
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Feb 11, 2022 11:14 AM |  |  | 2280361290
E024224_NPS10_RedwaterLat_GWD48360_MPID215903 | NDE, CE Samples, Welding, Initial Coating, TForm, QA/QC | POSTED & SENT | POSTED & SENT | PETRO SLEEVE | Done, Done, Done, Done, Done, Done | 2022-02-02 - 2022-02-02 | Natasha Pignalosa | TC ENERGY | EMAT |  | 54.40141321, -113.8307322 | 17.01 | 0 to 17.01 | 17.77 | 3.96 | E024224 | 4500439912 | 22-0016 |  | 2022 | Karelia Delgado Feb 15, 2022 02:41 PM | E024224_NPS10_RedwaterLat_GWD48360_MPID215903 |  |  | 14 |  | 2232005704
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| Initial Coating |  | Done | 2022-02-02 | 2022-02-02 | Natasha Pignalosa Feb 14, 2022 04:46 PM |  |  | 2243179441
| NDE |  | Done |  |  | Natasha Pignalosa Feb 14, 2022 04:46 PM |  |  | 2232005968
| CE Samples |  | Done |  |  | Natasha Pignalosa Feb 14, 2022 04:46 PM |  |  | 2232006327
| Welding |  | Done |  |  | Natasha Pignalosa Feb 14, 2022 04:46 PM |  |  | 2232006684
| TForm |  | Done |  |  | Ricardo Franklin Feb 15, 2022 02:42 PM |  |  | 2268635962
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Feb 14, 2022 04:46 PM |  |  | 2290899872
E024223_NPS6_ChardLat_MPID211806 _Lac La Biche 4 ECEA Dig #1 | NDE, CE Samples, Welding, TFORM, QA/QC | POSTED & SENT | POSTED & SENT | GRIND REPAIR | Done, Done, Done, Done, Done |  | David Hamelin, David Weaver, Ricardo Franklin, Natasha Pignalosa | TC ENERGY | EXT CORROSION |  | 55.847652, -110.682268 |  | '- | 3 | 4.78 | E024223 | 4500439911 | 22-0016 |  | 2022 | Ricardo Franklin Feb 16, 2022 12:49 PM | E024223_NPS6_ChardLat_MPID211806 _Lac La Biche 4 ECEA Dig #1 |  |  | 14 |  | 2243251632
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Hamelin, David Weaver | Done |  |  | Ricardo Franklin Feb 16, 2022 12:50 PM |  |  | 2243253345
| CE Samples |  | Done |  |  | Natasha Pignalosa Feb 14, 2022 04:48 PM |  |  | 2243253522
| Welding |  | Done |  |  | Natasha Pignalosa Feb 14, 2022 04:48 PM |  |  | 2243253794
| TFORM | Ricardo Franklin | Done |  |  | Ricardo Franklin Feb 16, 2022 12:49 PM |  |  | 2290905824
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Feb 16, 2022 12:31 PM |  |  | 2290906441
E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 | NDE, TForm, QA/QC | POSTED & SENT | POSTED & SENT | GRIND REPAIR | Done, Done, Done | 2022-02-08 - 2022-02-08, 2022-02-08 - 2022-02-16 | David Hamelin, David Weaver, Ricardo Franklin, Natasha Pignalosa | TC ENERGY | EXT CORROSION | 2022-02-08 | 55.853507, -110.706307 |  | '- | 3 | 3.96 | E024223 | 4500439911 | 22-0016 |  | 2022 | Natasha Pignalosa Feb 16, 2022 06:07 PM | E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 | 2022-02-22 |  | 14 |  | 2243251502
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Hamelin, David Weaver | Done | 2022-02-08 | 2022-02-08 | Lazaro Manzano Feb 15, 2022 04:24 PM |  |  | 2243253322
| TForm | Ricardo Franklin | Done | 2022-02-08 | 2022-02-16 | Ricardo Franklin Feb 16, 2022 09:38 AM |  |  | 2297018785
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Feb 17, 2022 09:48 AM |  |  | 2303387109
E024223_NPS10_RedwaterLat_GWD87840_MPID186439 | NDE, TForm, QA/QC | POSTED & SENT | POSTED & SENT | ARMOR WRAP | Done, Done, Done | 2022-02-20 - 2022-02-22, 2022-02-28 - 2022-03-01 | David Weaver, Alejandro Dannenberg, Karelia Delgado, Natasha Pignalosa | TC ENERGY | DENT | 2022-02-22 | 54.01977498, -113.1468341 | 17.637 | 14.09 to 16.09 | 2 | 3.96 | E024223 | 4500439911 | 22-0016 |  | 2022 | Karelia Delgado Mar 4, 2022 10:03 AM | E024223_NPS10_RedwaterLat_GWD87840_MPID186439 | 2022-03-08 |  | 14 |  | 2327962505
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Alejandro Dannenberg | Done | 2022-02-20 | 2022-02-22 | Ricardo Franklin Feb 22, 2022 11:54 AM |  |  | 2327964338
| TForm | Karelia Delgado | Done | 2022-02-28 | 2022-03-01 | Ricardo Franklin Mar 4, 2022 09:00 AM |  |  | 2328458939
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Mar 4, 2022 09:59 AM |  |  | 2359027020
E024223_NPS12_FlatLakeLat_GWD18450_MPID186939 | NDE, TForm, QA/QC | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done | 2022-02-22 - 2022-02-24, 2022-02-25 - 2022-03-01, 2022-03-01 - 2022-03-04 | David Weaver, Alejandro Dannenberg, Ricardo Franklin, Natasha Pignalosa | TC ENERGY | DENT | 2022-02-24 | 54.39969454, -112.5527756 | 19.592 | 5.251 to 7.806 | 2.56 | 4.78 | E024223 | 4500439911 | 22-0016 |  | 2022 | Ricardo Franklin Mar 4, 2022 11:59 AM | E024223_NPS12_FlatLakeLat_GWD18450_MPID186939 | 2022-03-10 |  | 14 |  | 2330388657
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Alejandro Dannenberg | Done | 2022-02-22 | 2022-02-24 | Simon Susac Feb 25, 2022 09:50 AM |  |  | 2330388843
| TForm | Ricardo Franklin | Done | 2022-02-25 | 2022-03-01 | Ricardo Franklin Mar 1, 2022 03:18 PM |  |  | 2344287600
| QA/QC | Natasha Pignalosa | Done | 2022-03-01 | 2022-03-04 | Ricardo Franklin Mar 4, 2022 11:59 AM |  |  | 2371221403
E024223_NPS4_CheechamWestLat_MPID211817_Lac La Biche 3 ECEA Dig #4 | NDE, TFORM, QA/QC | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done | 2022-02-25 - 2022-02-25 | David Weaver, Alejandro Dannenberg, Karelia Delgado, Natasha Pignalosa | TC ENERGY | EXT CORROSION | 2022-02-25 | 56.278329, -110.838935 |  | '- | 3 | 3.2 | E024223 | 4500439911 | 22-0016 |  | 2022 | Karelia Delgado Mar 4, 2022 04:01 PM | E024223_NPS4_CheechamWestLat_MPID211817_Lac La Biche 3 ECEA Dig #4 | 2022-02-25 |  |  |  | 2344270720
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | David Weaver, Alejandro Dannenberg | Done | 2022-02-25 | 2022-02-25 | Simon Susac Feb 25, 2022 03:33 PM |  |  | 2344270883
| TFORM | Karelia Delgado | Done |  |  | Natasha Pignalosa Mar 4, 2022 09:58 AM |  |  | 2366299761
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Mar 4, 2022 10:38 AM |  |  | 2375299638
E024224_NPS16_RedwaterLatExt_GWD7250_MPID204896 | NDE, TFORM, QA/QC | POSTED & SENT | POSTED & SENT | RECOAT | Done, Done, Done | 2022-02-27 - 2022-02-28 | Alejandro Dannenberg, David Weaver, Karelia Delgado, Natasha Pignalosa | TC ENERGY | EXT CORROSION | 2022-02-28 | 54.08983231, -112.4690653 | 16.932 | 0 to 16.932 | 17.01 | 3.96 | E024224 | 4500439912 | 22-0017 |  | 2022 | Karelia Delgado Mar 11, 2022 09:40 AM | E024224_NPS16_RedwaterLatExt_GWD7250_MPID204896 | 2022-03-14 |  | 14 |  | 2351780002
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| TFORM | Karelia Delgado | Done |  |  | Karelia Delgado Mar 9, 2022 05:04 PM |  |  | 2366261927
| NDE | Alejandro Dannenberg, David Weaver | Done | 2022-02-27 | 2022-02-28 | Simon Susac Mar 1, 2022 09:36 AM |  |  | 2351780182
| QA/QC | Natasha Pignalosa | Done |  |  | Natasha Pignalosa Mar 10, 2022 03:32 PM |  |  | 2402980968
E024223_NPS8_GlendonLatLoop_MPID211809_Lac La Biche 5 ECEA Dig #1 | NDE, TFORM | POSTED & SENT | POSTED & SENT | RECOAT | Done, Working On It | 2022-03-10 - 2022-03-11, 2022-03-14 - 2022-03-14 | Christian Forero, David Weaver, Karelia Delgado | TC ENERGY | EXT CORROSION | 2022-03-11 | 54.332344, -111.202619 |  | '- | 3 | 4.8 | E024223 | 4500439911 | 22-0016 |  | 2022 | Karelia Delgado Mar 16, 2022 04:42 PM | E024223_NPS8_GlendonLatLoop_MPID211809_Lac La Biche 5 ECEA Dig #1 | 2022-03-25 |  | 14 |  | 2402004255
Subitems | Name | Assigned Technicians | Status | NDE Timeline - Start | NDE Timeline - End | Last Updated | QAQC Timeline - Start | QAQC Timeline - End | Item ID (auto generated)
| NDE | Christian Forero, David Weaver | Done | 2022-03-10 | 2022-03-11 | Karelia Delgado Mar 16, 2022 03:22 PM |  |  | 2402004706
| TFORM | Karelia Delgado | Working On It | 2022-03-14 | 2022-03-14 | Karelia Delgado Mar 14, 2022 12:04 PM |  |  | 2408200498
[10 empty] | 2022-01-16 to 2022-03-14 | [12 empty] | 2022-01-30 to 2022-03-28 |  |  | 0

## 4_planning_pli-updates
4_Planning_PLI | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
2154235369 | E024223_NPS10_RedwaterLat_GWD10520_MPID216464 | Update |  | Simon Susac | 17/January/2022 11:59:32 AM | '@Zeeshan Shaikh ﻿ @Lazaro Manzano﻿ ﻿ this site is complete and ready for T-Forms reporting.﻿﻿ | 0 |  | 1317309295
2154235369 | E024223_NPS10_RedwaterLat_GWD10520_MPID216464 | Update |  | Simon Susac | 26/January/2022 10:19:00 AM | ﻿Hi @Zeeshan Shaikh﻿ ﻿ is there something that is preventing us from submitting this site to TCE? ﻿ ﻿CC @Lazaro Manzano﻿ ﻿﻿ | 0 |  | 1331131465
2154235369 | E024223_NPS10_RedwaterLat_GWD10520_MPID216464 |  | Reply | Zeeshan Shaikh | 26/January/2022 10:27:00 AM | ﻿Trying to locate in-house laser training certificate for Alejandro. Will upload as soon as I can track it down. | 0 |  | 1331149669 | 1331131465
2170098531 | E024224_NPS16_PeerlessLakeLat_GWD17960_MPID214468 | Update |  | Simon Susac | 26/January/2022 10:19:25 AM | '@Zeeshan Shaikh ﻿ same with this site? ﻿ ﻿Thanks ﻿ ﻿CC @Lazaro Manzano﻿ ﻿﻿﻿ | 0 |  | 1331132464
2170098531 | E024224_NPS16_PeerlessLakeLat_GWD17960_MPID214468 |  | Reply | Zeeshan Shaikh | 26/January/2022 10:26:22 AM | ﻿Pending final QA Review by Natasha. Will be uploaded end of day today. | 0 |  | 1331148310 | 1331132464
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 | Update |  | Simon Susac | 01/February/2022 10:21:46 AM | '@Ricardo Franklin ﻿@Kaidel Martinez﻿ ﻿@Lazaro Manzano﻿ @Zeeshan Shaikh﻿ ﻿﻿﻿ ﻿ ﻿This site is complete but we are still waiting on a repair recommendation from TCE | 1 |  | 1340965841
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Kaidel Martinez | 01/February/2022 11:09:10 AM | Repair Decision: Feb 01,2022 (Please recoate the dents, we will issue an EA to document the repair decision. ) as per ﻿﻿Rick Wang email. | 0 |  | 1341101976 | 1340965841
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Kaidel Martinez | 01/February/2022 11:10:49 AM | '@Ricardo Franklin ﻿I did the laser analysis for this site. ﻿ | 0 |  | 1341105713 | 1340965841
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Ricardo Franklin | 01/February/2022 11:22:53 AM | ﻿I am sorting the photos and preparing it for the photo album. | 1 |  | 1341132840 | 1340965841
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 | Update |  | Simon Susac | 03/February/2022 09:38:19 AM | '@Ricardo Franklin ﻿ can you change the status to 'Final Report In Progress' when you start working on the T-Form report? This way it won't sit in the active site and we will know that it is getting worked on. ﻿ ﻿Thanks! ﻿ | 0 |  | 1344870705
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Ricardo Franklin | 03/February/2022 09:41:03 AM | '@Simon Susac ﻿ sure thing! Actually I added the item of Final Report In Progress ﻿ | 0 |  | 1344880212 | 1344870705
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Simon Susac | 03/February/2022 09:41:33 AM | ﻿Great, thanks! | 0 |  | 1344881228 | 1344870705
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 | Update |  | Ricardo Franklin | 07/February/2022 09:26:57 AM | '@Natasha Pignalosa. ﻿In this TForm, in the Geometry tab I left the Dent Grind or Profile Complete? blank since it is empty on the field note, I was inclined to filled no but I wasn't sure.﻿﻿ | 0 |  | 1349253824
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Natasha Pignalosa | 07/February/2022 10:38:04 AM | ﻿Thanks, I'll take a look at it this afternoon. Looks like we have a little time on it. I'll try to have it to you for either end of day or early tomorrow. | 1 |  | 1349506711 | 1349253824
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 |  | Reply | Natasha Pignalosa | 07/February/2022 03:28:19 PM | '@Ricardo Franklin ﻿Can you send the field notes via email? I didn't see them attached in the form. Thanks!﻿ | 0 |  | 1350158682 | 1349253824
2177491938 | E024223_NPS10_RedwaterLat_GWD5610_MPID186438 | Update |  | Ricardo Franklin | 10/February/2022 02:56:56 PM | ﻿This site was submitted yesterday to TC Energy | 1 |  | 1356749749
2177492319 | E024223_NPS10_RedwaterLat_GWD7420_MPID215188 | Update |  | Natasha Pignalosa | 10/February/2022 03:51:06 PM | '@Ricardo Franklin ﻿Is this ready for review?﻿ | 0 |  | 1356868542
2177492319 | E024223_NPS10_RedwaterLat_GWD7420_MPID215188 |  | Reply | Ricardo Franklin | 10/February/2022 03:52:54 PM | ﻿Sorry @Natasha Pignalosa﻿ ﻿﻿, I didn't write you back,. The answer is yes, it is ready for review | 1 |  | 1356872074 | 1356868542
2232005704 | E024224_NPS10_RedwaterLat_GWD48360_MPID215903 | Update |  | Ricardo Franklin | 09/February/2022 09:20:12 AM | ﻿Karelia is working on this site. ﻿ | 0 |  | 1353475502
2237011531 | TCE STN 148 - NPS 36 Suction Line | Update |  | Simon Susac | 03/February/2022 09:39:57 AM | '@Natasha Pignalosa ﻿ has the T-Form pre-pop been submitted for this? It is the work that Rainier did at Station 148. ﻿ ﻿Thanks! | 0 |  | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Natasha Pignalosa | 03/February/2022 09:45:30 AM | According to my records, we submitted an excel version of this report through the online submission database back in August. Is this the same site that has now been repaired? I was only aware that we had been there on Tuesday. ﻿﻿ | 0 |  | 1344889995 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Kaidel Martinez | 08/February/2022 03:54:12 PM | '@Simon Susac ﻿, @Natasha Pignalosa﻿ ﻿ did you reached any conclusion? do we need to submit a TFORM for this?﻿﻿ | 0 |  | 1352294760 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Kaidel Martinez | 08/February/2022 03:55:27 PM | '@Ricardo Franklin ﻿Read above﻿ | 0 |  | 1352297046 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Natasha Pignalosa | 08/February/2022 04:23:09 PM | '@Kaidel Martinez ﻿No, nothing was decided. I would suggest whoever is going to be taking care of TFORMs requesting going forward contact Pascal and ask him if they would want a new form or off the existing one we submitted via the Drive last year.﻿ | 1 |  | 1352385128 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Kaidel Martinez | 08/February/2022 04:40:47 PM | ﻿ok. thnks | 0 |  | 1352417411 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Lazaro Manzano | 16/February/2022 12:49:06 PM | '@Ricardo Franklin ﻿ see details here﻿ | 0 |  | 1365553921 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Ricardo Franklin | 02/March/2022 03:56:14 PM | '@Natasha Pignalosa ﻿this site was submitted today (March 02) as per instruction of Caroline Dawoud from TCE. ﻿﻿I drop everything on the TEC site and also sent mails, I haven't heard from them yet.﻿ | 0 |  | 1387493672 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Natasha Pignalosa | 03/March/2022 01:11:32 PM | '@Ricardo Franklin ﻿There was an email sent last night that we may have put it in the wrong folder. Please take a look and let the team know.﻿﻿ | 0 |  | 1389175051 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Kaidel Martinez | 03/March/2022 04:03:13 PM | ﻿I saw that email. I will verify with @Ricardo Franklin﻿ ﻿tomorrow morning﻿ | 0 |  | 1389501997 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Ricardo Franklin | 04/March/2022 09:52:16 AM | ﻿Hi @Kaidel Martinez﻿ ﻿and @Natasha Pignalosa﻿ ﻿﻿﻿, I am working on this as well as the mail sent yesterday by Pascal Yu. I will keep you posted on everything. | 1 |  | 1390524626 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line |  | Reply | Ricardo Franklin | 04/March/2022 10:33:57 AM | '@Kaidel Martinez ﻿@Natasha Pignalosa﻿ ﻿@Karelia Delgado﻿: This site is already uploaded as per recommendation from TC Energy.﻿﻿﻿ | 0 |  | 1390606613 | 1344876974
2237011531 | TCE STN 148 - NPS 36 Suction Line | Update |  | Natasha Pignalosa | 16/February/2022 02:15:53 PM | ﻿TFORMs request submitted. Report moved to high priority. | 0 |  | 1365735180
2237011531 | TCE STN 148 - NPS 36 Suction Line | Update |  | Ricardo Franklin | 04/March/2022 03:09:35 PM | Lachenaie Stn and STN 148 ---------- Forwarded message --------- From: Ricardo Franklin <rfranklin@ndtgroup.ca> Date: Fri, Mar 4, 2022 at 3:08 PM Subject: Lachenaie Stn and STN 148 To: <comp_doc_control@tcenergy.com>, Karelia Delgado <kdelgado@ndtgroup.ca>, Natasha Pignalosa <npignalosa@ndtgroup.ca>, TForms Team <tforms@ndtgroup.ca>, Kaidel Martinez <kmartinez@ndtgroup.ca> Hi I write to you to let you know that the project number M.001039 for Lachenaie Stn and STN 148 is already uploaded to the NDT Group sharepoint (NPS36 Suction Line GWCS1-CS2 T). If something else is needed please let me know Regards, Ricardo -- Ricardo Franklin Mergarejo. NDT Group Inc. 20 Roy Blvd, Unit 30/31 Brantford, Ontario N3R 7K2 rfranklin@ndtgroup.ca www.ndtgroup.ca Office: 519-304-9199 Cell: 647-450-6171 Notice of Confidentiality: The information transmitted is intended only for the person or entity to which it is addressed and may contain confidential and/or privileged material. Any review re-transmission dissemination or other use of or taking of any action in reliance upon this information by persons or entities other than the intended recipient is prohibited. If you received this in error please contact the sender immediately by return electronic transmission and then immediately delete this transmission including all attachments without copying distributing or disclosing same. -- Ricardo Franklin Mergarejo. NDT Group Inc. 20 Roy Blvd, Unit 30/31 Brantford, Ontario N3R 7K2 rfranklin@ndtgroup.ca www.ndtgroup.ca Office: 519-304-9199 Cell: 647-450-6171 Notice of Confidentiality: The information transmitted is intended only for the person or entity to which it is addressed and may contain confidential and/or privileged material. Any review re-transmission dissemination or other use of or taking of any action in reliance upon this information by persons or entities other than the intended recipient is prohibited. If you received this in error please contact the sender immediately by return electronic transmission and then immediately delete this transmission including all attachments without copying distributing or disclosing same. | 0 |  | 1391133356
2243251502 | E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 | Update |  | Kaidel Martinez | 08/February/2022 03:59:07 PM | '@Ricardo Franklin, as soon as you get an answer from Pascal Yu. Please verify this TForm too. ﻿ | 0 |  | 1352330986
2243251502 | E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 |  | Reply | Lazaro Manzano | 15/February/2022 02:19:00 PM | '@Ricardo Franklin ﻿is there any update on this, what is the status on this Site?﻿ | 0 |  | 1363751559 | 1352330986
2243251502 | E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 |  | Reply | Ricardo Franklin | 15/February/2022 02:22:03 PM | ﻿I asked to David Hamelin since there isn't any End of excavation mail but at the same time, in the field note it says that the End of inspection was on Feb 8. | 0 |  | 1363759236 | 1352330986
2243251502 | E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 |  | Reply | Ricardo Franklin | 15/February/2022 04:03:22 PM | '@Kaidel Martinez﻿, @Lazaro Manzano﻿ ﻿﻿﻿﻿ This was only a verification dig. Only the coating was assessed, and it ended the same day that started (Feb 08) ﻿TForm status: Only missing the Photo Album. ﻿ETA: Feb 16 should be sent it to QA/QC | 1 |  | 1363957404 | 1352330986
2243251502 | E024223_NPS6_ChardLat_MIPD211807_Lac La Biche 4 ECEA Dig #2 |  | Reply | Kaidel Martinez | 15/February/2022 04:08:10 PM | ﻿Great! | 0 |  | 1363965678 | 1352330986
2243251632 | E024223_NPS6_ChardLat_MPID211806 _Lac La Biche 4 ECEA Dig #1 | Update |  | Kaidel Martinez | 08/February/2022 03:57:47 PM | ﻿Problem finding the Associated TFORM , Email was sent by R.Franklin to Pascal Yu on Feb 08. | 0 |  | 1352301123
2243251632 | E024223_NPS6_ChardLat_MPID211806 _Lac La Biche 4 ECEA Dig #1 | Update |  | Natasha Pignalosa | 14/February/2022 04:47:41 PM | '@Ricardo Franklin ﻿I saw this come through for review, I might not be able to get to it tomorrow as I'm working on priority audit stuff in the office. I'll keep you posted when I start.﻿ | 0 |  | 1361992023
2243251632 | E024223_NPS6_ChardLat_MPID211806 _Lac La Biche 4 ECEA Dig #1 |  | Reply | Ricardo Franklin | 14/February/2022 06:30:53 PM | Thanks @Natasha Pignalosa, for the heads up. For this site we have plenty of time. So, when you have the time, check it out, in the meantime I will start working on the other site. | 0 |  | 1362135980 | 1361992023
2327962505 | E024223_NPS10_RedwaterLat_GWD87840_MPID186439 | Update |  | Natasha Pignalosa | 04/March/2022 09:59:51 AM | '@Karelia Delgado ﻿Can you please add the repair method to this site for our tracking. Thanks!﻿﻿ | 0 |  | 1390540522
2330388657 | E024223_NPS12_FlatLakeLat_GWD18450_MPID186939 | Update |  | Ricardo Franklin | 01/March/2022 03:19:20 PM | '@Natasha Pignalosa: This site is for review ﻿ ﻿cc: @Kaidel Martinez﻿ ﻿@Karelia Delgado﻿ ﻿﻿﻿ | 0 |  | 1385428763
2365098307 | E024223_NPS8_KinosisLat_MPID211813_Lac La Biche 3 ECEA Dig #2 | Update |  | Simon Susac | 03/March/2022 02:02:04 PM | ﻿Hi @Kaidel Martinez﻿ ﻿@Karelia Delgado﻿ ﻿@Ricardo Franklin﻿ ﻿@Lazaro Manzano﻿ ﻿, This is the last site on this rotation. The crew won't be returning until March 9th, so you won't see any more sites coming in until then. ﻿ ﻿Thanks for the great work on the reporting, the crew completed a lot of sites this week and you were all able to stay on top of it! ﻿ ﻿Simon | 0 |  | 1389268174
2365098307 | E024223_NPS8_KinosisLat_MPID211813_Lac La Biche 3 ECEA Dig #2 |  | Reply | Kaidel Martinez | 03/March/2022 04:01:52 PM | ﻿Thanks @Simon Susac﻿ ﻿﻿﻿ | 0 |  | 1389499279 | 1389268174
2415960074 | E024223_NPS6_GregoireLatSeg1_MPID211812_Lac La Biche 3 ECEA Dig #1 | Update |  | Simon Susac | 14/March/2022 02:51:55 PM | '@Eng. Team ﻿ this is 1 of the last 3 digs on this project (for now). There are 4 sites that have been postponed to the summer. ﻿ | 0 |  | 1405429928
2415960074 | E024223_NPS6_GregoireLatSeg1_MPID211812_Lac La Biche 3 ECEA Dig #1 |  | Reply | Kaidel Martinez | 15/March/2022 08:48:17 AM | ﻿noted thanks. | 0 |  | 1406783747 | 1405429928
2415960154 | E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 | Update |  | Simon Susac | 14/March/2022 02:52:32 PM | '@Eng. Team ﻿ 2 of 3 remaining digs. The order of MPID211814 and 211812 will depend on how construction progresses.﻿﻿ | 0 |  | 1405431168
2415960154 | E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 |  | Reply | Kaidel Martinez | 15/March/2022 08:48:26 AM | ﻿noted | 0 |  | 1406784081 | 1405431168
2415960154 | E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 |  | Reply | Ricardo Franklin | 15/March/2022 01:55:53 PM | ﻿Noted | 0 |  | 1407518007 | 1405431168
2415960154 | E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 | Update |  | Simon Susac | 18/March/2022 02:38:10 PM | ﻿My bad - site is still ongoing. | 0 |  | 1413163901
2415960154 | E024223_NPS6_GregoireLatSeg1_MPID211814_Lac La Biche 3 ECEA Dig #3 | Update |  | Simon Susac | 21/March/2022 09:22:50 AM | ﻿This site is done. There is a repair weld to be completed on a pipe support - but so far we don't have anything to do with it. | 0 |  | 1414942847
2415960276 | E024223_NPS8_GlendonLatLoop_MPID211810_Lac La Biche 5 ECEA Dig #2 | Update |  | Simon Susac | 14/March/2022 02:53:20 PM | '@Eng. Team ﻿ This ﻿should ﻿ be the last site of the rotation and this dig package until we get to the remaining 4 digs some time in the summer.﻿ | 0 |  | 1405432618
2415960276 | E024223_NPS8_GlendonLatLoop_MPID211810_Lac La Biche 5 ECEA Dig #2 |  | Reply | Kaidel Martinez | 15/March/2022 08:48:40 AM | ﻿noted | 0 |  | 1406784607 | 1405432618